## Cronograma por Atividade
Atento ASR Cloud - Cronograma de Configuracao MVP PoC
Horas por atividade, recurso Azure e perfil de analista ¦ Maio 2026
Fase | Recurso / Servico Azure | Atividade | Perfil Analista | Horas Estimadas | Dependencia | Semana | Observacoes
FASE 1: PLANEJAMENTO E DESIGN
| Geral | Kickoff tecnico e alinhamento de requisitos | Arquiteto Cloud | 4 | - | S1 | Reuniao com stakeholders Foursys + Atento
| Geral | Revisao da arquitetura C4 e ajustes para PoC | Arquiteto Cloud | 4 | - | S1 | Simplificar para cenario MVP
| Geral | Definicao do plano de enderecamento IP (VNet/subnets) | Arquiteto Cloud | 2 | - | S1 | Alinhar ranges com Atento (evitar conflito)
| Geral | Levantamento de pre-requisitos com Atento (Avaya, IPs, firewall) | Arquiteto Cloud | 4 | - | S1 | Dependencia critica do cliente
| Geral | Documentacao do plano de implementacao | Arquiteto Cloud | 4 | - | S1 | Checklist de recursos e ordem de deploy
FASE 2: PROVISIONAMENTO DE INFRAESTRUTURA BASE
| Azure Subscription | Criacao/config da subscription e Resource Groups | Cloud Engineer | 2 | - | S2 | Naming convention, tags, policies
| VNet + Subnets | Criar VNet 10.100.0.0/16 com subnets segmentadas | Cloud Engineer | 3 | Subscription | S2 | GatewaySubnet, Subnet-APIM, Subnet-App, Subnet-PE
| NSGs | Configurar Network Security Groups por subnet | Cloud Engineer | 3 | VNet | S2 | Rules: Allow Atento IPs, Deny all inbound
| Route Tables | Configurar tabelas de roteamento (UDR) | Cloud Engineer | 2 | VNet | S2 | Rotas para trafego VPN
| Key Vault | Provisionar Key Vault + Managed Identity | Cloud Engineer | 2 | Subscription | S2 | Soft-delete habilitado, access policies
| Key Vault | Armazenar certificados VPN e API keys | Cloud Engineer | 1 | Key Vault | S2 | Gerar e armazenar secrets
FASE 3: CONECTIVIDADE VPN
| VPN Gateway | Provisionar VPN Gateway VpnGw1AZ | Cloud Engineer | 2 | VNet | S2-S3 | Deploy demora ~30-45min; config apos
| VPN Gateway | Configurar Local Network Gateway (IPs Atento) | Cloud Engineer | 2 | VPN Gateway | S3 | Depende dos IPs fornecidos pela Atento
| VPN Gateway | Criar Connection S2S (IPSec/IKEv2) | Cloud Engineer | 2 | Local GW | S3 | Shared key, DH Group, cipher suite
| VPN Gateway | Teste de conectividade tunel VPN com Atento | Cloud Engineer | 4 | Connection | S3 | Validar ping, traceroute, latencia
| VPN Gateway | Troubleshooting e ajuste de parametros VPN | Cloud Engineer | 4 | Teste VPN | S3 | Buffer para problemas de firewall/NAT
| VPN Gateway | Configurar BGP (se aplicavel) | Arquiteto Cloud | 2 | Connection | S3 | ASN, peering addresses
FASE 4: SERVICOS DE DADOS E SEGURANCA
| Redis Cache | Provisionar Azure Cache for Redis Standard C0 | Cloud Engineer | 1 | VNet | S3 | Standard para suporte a PE
| Redis Cache | Configurar Private Endpoint do Redis | Cloud Engineer | 1 | Redis | S3 | DNS privado + NSG
| Redis Cache | Configurar firewall rules e acesso VNet | Cloud Engineer | 1 | Redis PE | S3 | Bloquear acesso publico
| Private Endpoints | Criar PE para Speech Services | Cloud Engineer | 1 | Speech Svc | S3 | Private DNS Zone + link
| Private Endpoints | Validar resolucao DNS privada (todos PEs) | Cloud Engineer | 2 | Todos PEs | S3 | nslookup, teste de conectividade interna
FASE 5: API MANAGEMENT
| API Management | Provisionar APIM Developer tier | Cloud Engineer | 2 | VNet | S3 | Deploy demora ~30-40min
| API Management | Configurar VNet injection (internal mode) | Cloud Engineer | 3 | APIM | S3 | Subnet dedicada, NSG especifico
| API Management | Criar API definitions e operacoes (WebSocket) | Desenvolvedor Backend | 4 | APIM VNet | S4 | Endpoint /asr/transcribe
| API Management | Configurar policies (rate-limit, auth, CORS, logging) | Desenvolvedor Backend | 3 | API defs | S4 | API Key validation, IP filter
| API Management | Testar fluxo APIM -> backend (VM) | Desenvolvedor Backend | 2 | Policies | S4 | Validar roteamento e auth
FASE 6: COMPUTE (VM)
| Virtual Machine | Provisionar VM D2s v3 (Linux) na subnet | Cloud Engineer | 2 | VNet | S3 | Ubuntu 22.04 LTS, SSH key
| Virtual Machine | Hardening do OS (updates, firewall, SSH) | Cloud Engineer | 2 | VM | S3 | Desabilitar senha, apenas SSH key
| Virtual Machine | Instalar runtime (.NET / Node.js) e dependencias | Cloud Engineer | 2 | VM hardened | S3 | SDK do Speech, runtime da app
| Virtual Machine | Configurar Managed Identity e acesso ao Key Vault | Cloud Engineer | 1 | VM + KV | S3 | System-assigned identity
| Virtual Machine | Configurar scripts de deploy e restart | Cloud Engineer | 2 | Runtime | S4 | Systemd service, auto-start
FASE 7: SPEECH SERVICES E CUSTOM MODEL
| Speech Services | Provisionar Azure Speech Services (S0) em Brazil South | Cloud Engineer | 1 | Subscription | S2 | Verificar disponibilidade na regiao
| Speech Services | Configurar Private Endpoint do Speech | Cloud Engineer | 1 | Speech Svc | S3 | Private DNS Zone
| Custom Speech Model | Preparar dataset de treinamento (CNPJs alfanumericos) | Desenvolvedor Backend | 8 | - | S2-S3 | Gravar/sintetizar audios com variacoes foneticas
| Custom Speech Model | Treinar Custom Speech Model pt-BR | Desenvolvedor Backend | 4 | Dataset | S3-S4 | Upload dataset, configurar treinamento
| Custom Speech Model | Avaliar acuracia do modelo (WER/CER) | Desenvolvedor Backend | 4 | Modelo treinado | S4 | Testar com CNPJs reais e variantes
| Custom Speech Model | Deploy do Custom endpoint | Desenvolvedor Backend | 2 | Modelo aprovado | S4 | Endpoint dedicado para inferencia
| Custom Speech Model | Re-treino e ajustes (iteracao) | Desenvolvedor Backend | 8 | Avaliacao | S4-S5 | Buffer para melhorar acuracia
FASE 8: DESENVOLVIMENTO DA APLICACAO ASR
| ASR Orchestrator | Desenvolver WebSocket Handler (receber audio stream) | Desenvolvedor Backend | 12 | VM + APIM | S3-S4 | ASP.NET Core ou Node.js
| ASR Orchestrator | Desenvolver Speech Client (integracao Speech SDK) | Desenvolvedor Backend | 8 | Speech Svc | S4 | Real-time STT, resultados parciais/finais
| ASR Orchestrator | Desenvolver Audio Preprocessor (G.711 -> PCM 16kHz) | Desenvolvedor Backend | 6 | WS Handler | S4 | Conversao de codec, VAD
| ASR Orchestrator | Desenvolver CNPJ Parser (texto -> CNPJ alfanumerico) | Desenvolvedor Backend | 8 | Speech Client | S4-S5 | Heuristicas foneticas, normalizacao
| ASR Orchestrator | Desenvolver CNPJ Validator (digitos verificadores) | Desenvolvedor Backend | 4 | Parser | S5 | Algoritmo novo CNPJ alfanumerico
| ASR Orchestrator | Desenvolver Retry & Fallback Handler | Desenvolvedor Backend | 4 | Validator | S5 | Max 3 tentativas, fallback para operador
| ASR Orchestrator | Desenvolver Response Builder (JSON estruturado) | Desenvolvedor Backend | 2 | Retry | S5 | CNPJ, confianca, status
| ASR Orchestrator | Integrar App Insights SDK (telemetria) | Desenvolvedor Backend | 3 | App base | S5 | Metricas de latencia, erros, throughput
| ASR Orchestrator | Integrar Redis para session cache | Desenvolvedor Backend | 3 | Redis PE | S5 | Sessao por call-id
FASE 9: OBSERVABILIDADE
| Azure Monitor | Criar Log Analytics Workspace | Cloud Engineer | 1 | Subscription | S4 | Retencao 30 dias
| App Insights | Configurar Application Insights + connection string | Cloud Engineer | 1 | Log Analytics | S4 | Linked ao workspace
| Azure Monitor | Criar alertas criticos (VPN down, latencia, error rate) | Cloud Engineer | 2 | App Insights | S5 | Action group: email/SMS
| Azure Monitor | Criar dashboard operacional basico | Cloud Engineer | 2 | Metricas | S5 | KPIs: latencia, taxa ASR, erros
FASE 10: INTEGRACAO E TESTES END-TO-END
| Integracao Avaya | Configurar SBC para enviar audio via VPN/WebSocket | Arquiteto Cloud | 8 | VPN + App | S5-S6 | Depende da equipe Atento
| Integracao Avaya | Testar fluxo completo: URA -> VPN -> APIM -> ASR -> resposta | Arquiteto Cloud | 6 | Integracao | S6 | Ligacao real com CNPJ de teste
| Teste E2E | Testes funcionais com diferentes CNPJs alfanumericos | QA / Tester | 8 | Integracao OK | S6 | Cenarios: sucesso, retry, fallback
| Teste E2E | Testes de latencia (medir E2E < 1s) | QA / Tester | 4 | Funcional OK | S6 | Medir cada etapa do pipeline
| Teste E2E | Testes com sotaques regionais e ruido de fundo | QA / Tester | 4 | Funcional OK | S6 | SP, RJ, NE, Sul
| Teste E2E | Testes de resiliencia (derrubar componentes) | QA / Tester | 4 | Funcional OK | S6-S7 | VM restart, Redis flush, VPN drop
| Geral | Documentacao tecnica e handover | Arquiteto Cloud | 4 | Testes OK | S7 | Runbook operacional, diagrama atualizado
| Geral | Apresentacao de resultados e proximos passos | Arquiteto Cloud | 2 | Doc | S7 | Reuniao com Atento
TOTAL GERAL DE HORAS |  |  |  | 200

## Resumo por Perfil
Resumo de Horas por Perfil de Analista
Perfil do Analista | Horas Totais | Semanas Alocadas | Custo Estimado (ref)
SRE Cloud | 40 | 1 Semana | Planejamento, VPN, integracao Avaya, documentacao
Cloud Engineer / DevOps | 40 | 1 Semana | Provisionamento Azure, IaC, networking, seguranca
Desenvolvedor Backend (Senior) | 80 | 2 Semanas | Codigo ASR Orchestrator, Speech SDK, Custom Model
QA / Tester | 40 | 1 Semana | Testes E2E, latencia, resiliencia, sotaques
TOTAL | 200 | 5 Semanas
Premissas:
- Semana de 40h (8h/dia x 5 dias)
- Atividades podem ser paralelas entre perfis diferentes
- Duracao total estimada: 6-7 semanas (com paralelismo)
- Dependencia critica: informacoes tecnicas da Atento (IPs, Avaya, firewall)
- Custom Speech Model pode exigir iteracoes adicionais se acuracia < 85%

## Resumo por Recurso Azure
Horas de Configuracao por Recurso Azure
Recurso Azure | Horas Config. | Horas Desenvolvimento | Horas Total
Planejamento / Design Geral | 18 | 0 | 18
Azure Subscription + Resource Groups | 2 | 0 | 2
VNet + Subnets + NSGs + Route Tables | 8 | 0 | 8
VPN Gateway (S2S + BGP + testes) | 16 | 0 | 16
Key Vault + Managed Identity | 3 | 0 | 3
Redis Cache + Private Endpoint | 3 | 0 | 3
Private Endpoints (todos) + DNS | 3 | 0 | 3
API Management Developer (VNet injection) | 5 | 9 | 14
Virtual Machine D2s v3 (setup + hardening) | 9 | 0 | 9
Speech Services + Custom Model | 2 | 26 | 28
ASR Orchestrator (codigo da aplicacao) | 0 | 50 | 50
Azure Monitor + App Insights + Alertas | 6 | 0 | 6
Integracao Avaya (com equipe Atento) | 0 | 14 | 14
Testes E2E + Documentacao | 0 | 26 | 26
TOTAL | 75 | 125 | 200
Config. = provisionamento e configuracao de infra Azure
Desenvolvimento = codigo, integracao, treinamento ML, testes

## Timeline Semanal
Timeline de Execucao - MVP PoC (7 semanas)
Fase / Atividade | S1 | S2 | S3 | S4 | S5 | S6 | S7 | Perfil Principal
1. Planejamento e Design | X | [6 empty] | Arquiteto Cloud
2. Subscription + VNet + NSGs |  | X | [5 empty] | Cloud Engineer
3. Key Vault + Secrets |  | X | [5 empty] | Cloud Engineer
4. VPN Gateway + Tunel S2S |  | X | X |  |  |  |  | Cloud Engineer
5. Teste conectividade VPN |  |  | X |  |  |  |  | Cloud Engineer + Atento
6. Speech Services + PE |  | X | X |  |  |  |  | Cloud Engineer
7. Redis Cache + PE |  |  | X |  |  |  |  | Cloud Engineer
8. API Management Developer |  |  | X | X |  |  |  | Cloud Engineer
9. VM D2s v3 (setup + hardening) |  |  | X |  |  |  |  | Cloud Engineer
10. Custom Speech Model (treino) |  | X | X | X | X |  |  | Desenvolvedor Backend
11. ASR Orchestrator (codigo) |  |  | X | X | X |  |  | Desenvolvedor Backend
12. APIM Policies + APIs |  |  |  | X |  |  |  | Desenvolvedor Backend
13. Observabilidade (Monitor/Alerts) |  |  |  | X | X |  |  | Cloud Engineer
14. Integracao Avaya |  |  |  |  | X | X |  | Arquiteto + Atento
15. Testes E2E + Validacao | [5 empty] | X | X | QA / Tester
16. Documentacao + Handover | [6 empty] | X | Arquiteto Cloud